## Defect Log
Defect ID | Linked Test Case | Title | Description | Steps to Reproduce | Severity | Priority | Status | Root Cause Category | Reported By | Reported Date | Assigned To | Resolution
DEF-001 | TC-007 | Timeout transfer not set to Pending | When the real-time rail does not acknowledge a transfer within 30 seconds, the transfer remains in 'Processing' instead of transitioning to 'Pending', and the customer is not notified. | 1) Configure the rail simulator to not respond; 2) Submit an off-us transfer; 3) Wait 60 seconds; 4) Observe the status | Major | High | Open | Functional | M. Chen | 2026-10-22 | IT / Engineering | Pending fix; timeout handler to transition status and trigger notification
DEF-002 | TC-010 | Personal daily limit not enforced | A customer-configured personal daily limit is saved but is not applied during transfer validation; transfers above the personal limit are processed successfully. | 1) Set a personal daily limit of 2,000.00; 2) Attempt a 3,000.00 transfer in the same day; 3) Observe that the transfer is processed | Major | High | Open | Functional | M. Chen | 2026-10-22 | IT / Engineering | Pending fix; transfer validation must consider the effective limit
DEF-003 | TC-012 | Fraud high-risk profile cannot be activated in UAT | The fraud engine UAT instance does not allow enabling the high-risk profile, which blocks execution of the high-risk hold scenario. | 1) Open the fraud engine UAT settings; 2) Attempt to enable the high-risk profile; 3) Profile is not selectable | Critical | High | Open | Environment | L. Novak | 2026-10-23 | Fraud & Risk | Configuration access requested; profile to be enabled for retest
DEF-004 | TC-013 | Push notification not delivered on success | For a successful transfer, the email notification is received but the push notification is not delivered to the registered device. | 1) Complete a successful transfer; 2) Check the registered device for a push notification; 3) Only the email is received | Minor | Medium | Open | Integration | M. Chen | 2026-10-23 | IT / Engineering | Pending fix; notification service push channel under investigation
DEF-005 | TC-016 | Receipt shows wrong currency and misses reference | The downloadable transfer receipt displays the amount with the wrong currency symbol and omits the transfer reference. | 1) Open transfer history; 2) Download a receipt; 3) Inspect the currency symbol and reference | Minor | Medium | In Progress | UI / Data | M. Chen | 2026-10-24 | IT / Engineering | Fixing template mapping; retest scheduled
DEF-006 | TC-002 | Incorrect insufficient-balance error message | When a transfer is rejected for insufficient balance, the message shown is 'Funds unavailable' instead of the agreed copy 'Insufficient available balance'. | 1) Set available balance to 100.00; 2) Attempt a 150.00 transfer; 3) Read the error message | Trivial | Low | Open | Content / Copy | M. Chen | 2026-10-20 | IT / Engineering | Pending fix; error catalogue to be updated