## Test Cases
Test Case ID | Title | User Story | Requirement | Type | Priority | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Defect ID | Executed By | Execution Date
TC-001 | Complete transfer to a saved beneficiary | US-01 | FR-01 | Functional | P1 | Customer is authenticated; account NB-UAT-ACC-001 has available balance 1,500.00; beneficiary NB-UAT-BEN-001 'Maria Lopez' is saved and active | 1) Open Instant Transfer; 2) Select saved beneficiary 'Maria Lopez'; 3) Enter amount 250.00; 4) Confirm transfer | Amount 250.00; beneficiary NB-UAT-BEN-001 | Transfer accepted; 250.00 debited; confirmation shows a unique reference; status Completed | As expected | Pass |  | A. Rivera | 2026-10-20
TC-002 | Reject transfer with insufficient balance | US-01 | FR-01, FR-02 | Negative | P1 | Customer is authenticated; account NB-UAT-ACC-002 has available balance 100.00; beneficiary NB-UAT-BEN-001 is saved | 1) Open Instant Transfer; 2) Select saved beneficiary; 3) Enter amount 150.00; 4) Confirm transfer | Amount 150.00 | Transfer rejected; message 'Insufficient available balance' shown; no debit; balance unchanged | Rejected as expected, but the error text read 'Funds unavailable' instead of the agreed message | Pass | DEF-006 | M. Chen | 2026-10-20
TC-003 | Add a new beneficiary with re-authentication | US-02 | FR-01, FR-10 | Functional | P1 | Customer is authenticated | 1) Add a new beneficiary with valid account details; 2) Submit the form; 3) Complete re-authentication when prompted | Beneficiary account NB-UAT-BEN-002 | Re-authentication requested; after success the beneficiary is saved and available for future transfers | As expected | Pass |  | A. Rivera | 2026-10-20
TC-004 | Block beneficiary failing sanctions screening | US-02 | FR-10, BR-RULE-04, BR-RULE-10 | Security | P1 | Customer is authenticated; sanctions screening is active in UAT | 1) Add a beneficiary matching a sanctions list entry; 2) Submit and let screening run | Beneficiary account NB-UAT-BEN-SAN-01 | Beneficiary blocked; message 'We cannot process transfers to this beneficiary' shown; event reported to Compliance; beneficiary not available | As expected | Pass |  | L. Novak | 2026-10-21
TC-005 | On-us transfer settles in under 10 seconds | US-03 | FR-03, FR-06 | Non-functional | P1 | Both sender and beneficiary hold NovaBank accounts and are funded | 1) Open Instant Transfer; 2) Select an on-us beneficiary; 3) Enter amount 100.00; 4) Confirm and measure settlement time | Amount 100.00; on-us beneficiary NB-UAT-BEN-003 | Transfer settles in under 10 seconds; beneficiary balance increases by 100.00; status Completed | Settled in 3.2 seconds | Pass |  | M. Chen | 2026-10-21
TC-006 | Off-us transfer accepted by the rail | US-04 | FR-03 | Integration | P1 | Beneficiary account is held at a participating bank; rail simulator is available | 1) Open Instant Transfer; 2) Select an off-us beneficiary; 3) Enter amount 300.00; 4) Confirm and observe the rail acknowledgement | Amount 300.00; off-us beneficiary NB-UAT-BEN-004 | Transfer submitted to the real-time rail; on acknowledgement status becomes Completed | As expected | Pass |  | L. Novak | 2026-10-21
TC-007 | Off-us transfer rail timeout becomes Pending | US-04 | FR-06, BR-RULE-06 | Negative | P1 | Rail simulator is configured to not acknowledge the transfer | 1) Submit an off-us transfer of 300.00; 2) Wait more than 30 seconds; 3) Check transfer status and notifications | Amount 300.00; off-us beneficiary NB-UAT-BEN-004 | Status becomes 'Pending'; transfer queued for reconciliation; customer notified that the transfer is pending | Status stayed 'Processing' and never changed to Pending after 60 seconds; no pending notification was sent | Fail | DEF-001 | M. Chen | 2026-10-22
TC-008 | Reject amount below the minimum | US-05 | FR-04, BR-RULE-01 | Negative | P2 | Account has available balance 1,000.00 | 1) Initiate a transfer; 2) Enter amount 0.50; 3) Confirm | Amount 0.50 | Transfer rejected because the amount is below the 1.00 minimum; no debit | As expected | Pass |  | A. Rivera | 2026-10-22
TC-009 | Reject amount above available balance | US-05 | FR-04, BR-RULE-03 | Negative | P1 | Account NB-UAT-ACC-001 has available balance 1,000.00 | 1) Initiate a transfer; 2) Enter amount 2,000.00; 3) Confirm | Amount 2,000.00 | Transfer rejected for exceeding the available balance; no debit; balance unchanged | As expected | Pass |  | L. Novak | 2026-10-22
TC-010 | Enforce and configure daily limits | US-05 | FR-04, FR-11, BR-RULE-02 | Functional | P1 | Account has default daily limit 20,000.00 | 1) Open limit settings; 2) Set a personal daily limit of 2,000.00; 3) Attempt a transfer of 3,000.00 the same day; 4) Confirm | Personal daily limit 2,000.00; attempted amount 3,000.00 | Transfer rejected for exceeding the daily limit; the new limit is confirmed to the customer | Personal limit was saved, but a 3,000.00 transfer was processed successfully, exceeding the configured limit | Fail | DEF-002 | M. Chen | 2026-10-22
TC-011 | Low-risk transfer passes fraud screening | US-06 | FR-05 | Functional | P1 | Fraud engine is configured to score the transfer as low risk | 1) Initiate a transfer of 120.00; 2) Confirm and observe the fraud decision | Amount 120.00; low-risk profile | Transfer proceeds to settlement without additional checks; status Completed | As expected | Pass |  | A. Rivera | 2026-10-22
TC-012 | High-risk transfer held for review | US-06 | FR-05, BR-RULE-05 | Functional | P1 | Fraud engine must be configured to score the transfer as high risk | 1) Configure the high-risk profile; 2) Initiate a transfer of 4,500.00; 3) Confirm and observe the outcome | Amount 4,500.00; high-risk profile | Status 'Held for review'; funds not debited; customer notified that the transfer is under review | Could not execute: the fraud engine UAT rules could not be activated during the test window | Blocked | DEF-003 | L. Novak | 2026-10-23
TC-013 | Customer receives outcome notification | US-07 | FR-07 | Functional | P2 | Customer has a registered device and email | 1) Complete a successful transfer; 2) Check the device for a push notification; 3) Check the email inbox | Amount 80.00; notification channels registered | Push notification and email received, including amount, beneficiary and reference | Email received, but no push notification was delivered for the successful transfer | Fail | DEF-004 | M. Chen | 2026-10-23
TC-014 | Rail rejection releases funds | US-08 | FR-09 | Negative | P1 | Rail simulator is configured to reject the transfer | 1) Submit an off-us transfer of 250.00; 2) Observe the rail response; 3) Check the account balance and notification | Amount 250.00; rail rejects | Status 'Rejected'; no funds debited; customer notified with the rejection reason | As expected | Pass |  | A. Rivera | 2026-10-23
TC-015 | Returned transfer credited within 1 business day | US-08 | FR-09, BR-RULE-07 | Integration | P1 | A previously settled off-us transfer exists and the receiving bank returns it | 1) Process the return from the receiving bank; 2) Check the sender account balance and notification | Returned amount 250.00 | Funds credited back to the sender within 1 business day; customer notified of the return | Funds credited back within 2 hours; customer notified | Pass |  | L. Novak | 2026-10-23
TC-016 | Filter history and download a receipt | US-09 | FR-08 | UI | P3 | Customer has several completed transfers | 1) Open transfer history; 2) Filter by status 'Completed'; 3) Download the receipt for a transfer | Filter 'Completed'; receipt for transfer NB-UAT-TRN-0142 | Only completed transfers listed with date, beneficiary, amount and status; receipt contains reference, amount and timestamp | Filter works, but the downloaded receipt shows the amount with the wrong currency symbol and omits the transfer reference | Fail | DEF-005 | M. Chen | 2026-10-24
TC-017 | Operations search pending transfers | US-10 | FR-12 | Functional | P2 | Operations user is authenticated; at least one pending transfer exists | 1) Log in to the operations back-office; 2) Filter transfers by status 'Pending' and age greater than 5 minutes | Pending transfer NB-UAT-TRN-0231 | Matching transfers are listed with their references and age | As expected | Pass |  | A. Rivera | 2026-10-24
TC-018 | Operations manually resolve a pending transfer | US-10 | FR-12, BR-RULE-06 | Functional | P2 | A transfer with status 'Pending' exists | 1) Open the pending transfer; 2) Confirm it was not settled at the rail; 3) Mark the transfer as 'Rejected' | Pending transfer NB-UAT-TRN-0231 | Transfer marked 'Rejected'; funds released back to the customer; customer notified | As expected | Pass |  | L. Novak | 2026-10-24